## Q&A Log
Q & A Document
No. | File / Class / Document | Page / Section / Line Number | Question / Clarification | Raised By | Raised On | Clarification Description | Clarified By | Clarified On | Priority | Status
1 | SPPM (system) | Employee Management | 1. Search employee function not working | Shehani | 2019-08-09 | It was searching with the exact keyword, now searching with 'LIKE' query | Udana | 2019-08-14 | High | Fixed
2 |  | Employee Management | 1.Update employee details function not working. When click on tables details will not dispay in textboxes. | Shehani | 2019-08-09 | You have to click on the employee and select update | Udana | 2019-08-14 | High | Closed
3 |  | Admin Manage | 1. Validatios are not implemented in add new admin function | Shehani | 2019-08-09 | Implemented | Udana | 2019-08-14 | Medium | Fixed
4 |  | Forgot password | 1. Not implemented yet | Shehani | 2019-08-09 | Implemented | Udana | 2019-08-14 | High | Fixed
5 |  | Client management | 1. when adding new client error message will not be prompted if text boxes are empty | Shehani | 2019-08-09 | Sorted | Udana | 2019-08-14 | Medium | Fixed
6 |  | Login | 1.Password is not hidden | Shehani | 2019-08-09 | Changed to Password Field | Udana | 2019-08-14 | Medium | Fixed
7 |  | Client management > update > client profile | 1. Client profile is not updating | Shehani | 2019-08-10 | Had a SQL Error | Udana | 2019-08-14 | High | Fixed
8 |  | Client management > update > client profile > Back | 1. Back button redirects to employee management interface. It should navigates to client management interface | Shehani | 2019-08-10 | Had a SQL Error | Udana | 2019-08-14 | High | Fixed
9 |  | Admin Manage | 1. Validatios are not implemented in add new admin function | Shehani | 2019-08-09 | Implemented | Udana | 2019-08-14 | Medium | Fixed
10 |  | Client management > delete | 1. Delete confirmation box is not displayed | Shehani | 2019-08-10 | Box added | Udana | 2019-08-15 | Low | Fixed
11 |  | Finance Management | 1. Total balance is wrong. Total balance should be = total income - total expenses | Shehani | 2019-08-10 | Fixed | Melaka | 2019-08-15 | High | Fixed
12 |  | Finance Management | 1. Database is not updating If text boxes are empty or invalid type of data, but there should be an proper error message. | Shehani | 2019-08-10 | Validated | Melaka | 2019-08-15 | Low | Fixed
13 |  | Finance Management > Generate Report > Pie Chart > Send Mail | 1. Email of pie chart is not sending to the user | Shehani | 2019-08-10 |  |  |  | Medium | Open
14 |  | Project Management | 1. Data will be added into the DB even project name is empty | Shehani | 2019-08-10 | Validated | Udana | 2019-08-15 | High | Fixed
15 |  | Project Management | 1. Does not show confirmation boxes for updating and deleting | Shehani | 2019-08-10 | Validated | Udana | 2019-08-15 | Low | Fixed
16 |  | Project Management | 1. Update function does not work | Shehani | 2019-08-10 | Bugs fixed | Udana | 2019-08-15 | High | Fixed
17 |  | Project Management | 1. Email od PDF is not sending to the user | Shehani | 2019-08-10 |  |  |  | Medium | Open
18 |  | Employee Manage | 1. The system doen not display any error essages if text boxes are empty or invalid data type | Shehani | 2019-08-11 | Validated | Udana | 2019-08-15 | Medium | Fixed
19 |  | Employee Manage | 1. Does not display data on text boxes when the user click on data on the table. | Shehani | 2019-08-11 | You have to click on update to update values | Udana | 2019-08-15 | Medium | Closed
20 |  | Employee Manage | 1. Does not display an confirmation boxes when updating or deleting | Shehani | 2019-08-11 | Validated | Udana | 2019-08-15 | Low | Fixed
21 |  | Employee Profile | 1. when click on back button employee manage page will open. There should be a way to go back to the manager interface. | Shehani | 2019-08-11 | Bugs fixed | Udana | 2019-08-15 | Low | Fixed